## Risks
# | Risk Description | Probability (Low Estimate) | Probability (High Estimate) | Consequence Range (Low Estimate) | Consequence Range (High Estimate) | Risk (Low Estimate) | Risk (High Estimate) | Risk (Mean) | Risk (Variance)
1 | Data files are received from the client a week later than expected | 0.1 | 0.3 | 10 | 20 | 1 | 6 | 3.5 | 6.25
2 | Software development team is swamped and implementation does not occur on schedule | 0.2 | 0.5 | 20 | 40 | 4 | 20 | 12 | 64
3 | Software development team does not sufficiently understand the machine learning algorithm | 0.05 | 0.15 | 2 | 8 | 0.1 | 1.2 | 0.65 | 0.3025
4 | Client is not ready to receive the updated software | 0.15 | 0.3 | 10 | 40 | 1.5 | 12 | 6.75 | 27.5625
T | Deadline Prediction | [6 empty] | 22.9 | 9.9053

## DeadlinePrediction
Time (Hours) | Risk
1 | 0.003496
2 | 0.0043481
3 | 0.005353
4 | 0.0065233
5 | 0.0078689
6 | 0.0093958
7 | 0.011105
8 | 0.012992
9 | 0.015046
10 | 0.017248
11 | 0.019572
12 | 0.021983
13 | 0.024441
14 | 0.026899
15 | 0.029303
16 | 0.031599
17 | 0.033729
18 | 0.035637
19 | 0.037272
20 | 0.038586
21 | 0.039541
22 | 0.04011
23 | 0.040274
24 | 0.040028
25 | 0.039381
26 | 0.038351
27 | 0.036969
28 | 0.035276
29 | 0.033319
30 | 0.031151
31 | 0.028829
32 | 0.02641
33 | 0.023948
34 | 0.021496
35 | 0.019099
36 | 0.016797
37 | 0.014623
38 | 0.012601
39 | 0.010749
40 | 0.0090758
41 | 0.0075854
42 | 0.0062755
43 | 0.0051391
44 | 0.0041659
45 | 0.0033427
46 | 0.002655
47 | 0.0020874
48 | 0.0016245
49 | 0.0012514
50 | 0.00095423
51 | 0.00072025
52 | 0.00053813
53 | 0.00039799
54 | 0.00029135
55 | 0.00021113
56 | 0.00015144
57 | 0.00010753
58 | 7.5573e-05
59 | 5.2576e-05
60 | 3.6206e-05